## Slide 1: CONTEMPORARY PROJECT MANAGEMENT, 4E
Timothy J. Kloppenborg
Vittal Anantatmula
Kathryn N. Wells

## Slide 2: Project Risk Planning
Chapter 11

## Slide 3: Chapter 11 Core Objectives:
Describe how to plan for risk management, identify risks, analyze risks, & create risk response plans for identified risks
Identify and classify risks for a project & populate a risk register
Describe various risk assessment techniques & when they are appropriate
Prioritize project risks, using appropriate assessment techniques
Compare & contrast strategies for dealing with risks

## Slide 4: Chapter 11 Technical Objectives:
Select & utilize an appropriate quantitative risk analysis tool if qualitative risk analysis is not sufficient

## Slide 5: Chapter 11 Behavioral Objectives:
Determine an individual’s propensity to accept risk & use that to strategize about which risks to accept
Determine an organization’s propensity to accept risk & use that knowledge to strategize about which risks to accept

## Slide 6: Texas Medical Center
Rhonda Wendler
Texas Medical Center News
“While project managers cannot prevent hurricanes, through careful risk planning, actions can be taken to greatly mitigate the impact.”

## Slide 7: Project Risk Planning
Approach to risk is same on any project:
  Identify
  Assess
  Respond
Level of depth/energy expended on risk planning varies greatly among projects
Purpose of risk management is to reduce overall project risk to acceptable level (NOT to avoid risk entirely)
More detailed risk management in iteration planning, daily stand-up meetings, retrospectives

## Slide 8: Plan Risk Management
  Plan risk management – “the process of defining how to conduct risk management activities for a project.” ~Practice Standard for Project Risk Management (PMI)
A PM must understand success measures & priorities for a project in order to develop a risk management plan
Risk management plan decides details to approach, plan, & execute risk management activities

## Slide 9: Plan Risk Management
What constitutes project success?
  Meeting various agreements (i.e., contracts)
  Did project meet customers’ expectations?
  Did project help the performing organization?
    New technologies
    Employee growth

## Slide 10: Specific Project Stakeholder Priorities

## Slide 11: Risk Management Planning & Stakeholder Priorities
Understand what the project plan calls for
Understand area the most important stakeholders like to improve
Understand where stakeholders are willing to sacrifice to enable improvements

## Slide 12: Understanding the Project Risk
  threat – “a risk that will have a negative impact on the project objective if it occurs.” ~Practice Standard for Project Risk Management (PMI)
  opportunity – “a risk that would have a positive effect on one or more project objectives.” ~Practice Standard for Project Risk Management (PMI)
project risk – anything that may impact the project team’s ability to achieve the general project success measures and the specific project stakeholders’ priorities

## Slide 13: Plan Risk Management
Roles & Responsibilities
Categories & Definitions
Risk management plan– part of the project management plan that describes how risk management activities will be prioritized, monitored, planned & performed; also used for communicating with project stakeholders & for follow-up analysis

## Slide 14: Roles and Responsibilities
Encourage wide participation in risk management activities
More perspectives considered  more risks uncovered
Participation encourages buy-in to a risk management approach
Identify who is responsible for each risk

## Slide 15: Categories and Definitions
More project risks generally uncovered early in the life of a project
The cost per risk discovered early is less
Risks discovered late in a project can be expensive
Categorizing risks often leads to more thorough risk identification. Classify by:
  Stage of project lifecycle
  Project objective that would be impacted
  External vs. internal to project
  What is known vs. unknown (uncertainty)

## Slide 16: Risks Over the Project Life Cycle

## Slide 17: Categories and Definitions
A “known known” can be planned and managed with certainty
“Known unknowns” can be identified and may or may not happen
“Unknown unknowns” are true uncertainties
Cement will harden
Bad weather will happen
100-year flood

## Slide 18: Breakout Session!
Identify project risks you have encountered or may encountered, in each of the following categories:
  Known knowns
  Known unknowns
  Unknown unknowns
  Unknown Unknowns, by their very definition, may be hard to brainstorm….bragging rights go to the team with the most interesting/unique unk-unk!

## Slide 19: International Construction Project Risk Factors

## Slide 20: Top Risks for International Projects

## Slide 21: Top Risks for Software Projects

## Slide 22: Identify Risks
Information gathering
Reviews
Understanding Relationships
Risk register
  Identify risks – “the process of determining which risks might affect the project and documenting their characteristics.” ~Practice Standard for Project Risk Management (PMI)

## Slide 23: Information Gathering
Brainstorming activity considering “what could go wrong”
Variations & extensions of possible risks can help to identify additional risks
Interview stakeholders
SWOT analysis, Delphi technique

## Slide 24: Information Gathering
SWOT analysis – detailed analysis of project’s strengths, weaknesses, opportunities, & threats
  Delphi technique– an info gathering technique whose goal is to reach consensus among a group of experts; involves soliciting anonymous expert opinions, summarizing them, & sending them back to the experts for further comments and improvements

## Slide 25: Structured Reviews
Reviewing documents developed for the project & for other uses helps i.d. risks

## Slide 26: Understanding Relationships
Use a flow chart to learn the cause-and-effect relationships of risk events
Consider why a certain risk event may happen through root cause analysis
Root cause analysis – an analytical technique to ascertain the fundamental or causal reason(s) that affect one or more variances, defects, or risks.

## Slide 27: Understanding Relationships
Understand trigger conditions
A trigger may be specific to an individual risk
  Trigger condition – “a circumstance under which a risk strategy or risk action will be invoked.”
  ~Practice Standard for Project Risk Management (PMI)

## Slide 28: Risk Register
Primary output of risk identification…see Exhibit 11.9 in text
The risk register is a living document
Risk register – “the document containing the results of the qualitative risk analysis, quantitative risk analysis, and risk response planning. It identifies all identified risks, including description, category, cause, probability of occurring, impact(s) on objectives, proposed responses, owners, and current status.” ~Practice Standard for Project Risk Management (PMI)
Risk categories
Identified risks
Potential causes
Potential responses

## Slide 29: Breakout Session!
Begin compiling a risk register, similar to the example shown in Exhibit 11.9.
Remember that the risk register is a living document and will be added to/amended as the project proceeds.

## Slide 30: Risk Analysis
Understanding enough about each risk to determine how fully & formally it will be handled
  Perform Qualitative Risk Analysis
  Perform Quantitative Risk Analysis
  Risk Register Updates

## Slide 31: Perform qualitative Risk Analysis
How likely is this risk to happen?
How big will the impact be?
Qualitative risk analysis performed on all projects
Perform qualitative risk analysis – “the process of prioritizing risks for further analysis or action by assessing and combining their probability of occurrence and impact.”
~Practice Standard for Project Risk Management (PMI)

## Slide 32: Qualitative Risk Assessment
Differentiate between major & minor risks using probability, impact, & PM judgment…each major risk needs a contingency plan and single “owner”

## Slide 33: Qualitative Risk Analysis
Cause and effect relationships
  One way to assess magnitude of effect is to understand cause
  Part of root cause analysis
  Change the effect by changing the underlying cause
  Use a cause and effect diagram

## Slide 34: Cause and Effect Diagram
Why could methods be a cause?
Why could machines be a cause?
List the risk as the effect in a box at head of the fish
Name the big “bones”
Complete the smaller “bones”
Why could people be a cause?
Why could machines be a cause?

## Slide 35: Cause and Effect Diagram

## Slide 36: Perform Quantitative Risk Analysis
Bigger, riskier, more complex, more expensive projects  quantitative structured techniques
Use to predict the probabilities
  Quantitative risk analysis – “the process of numerically analyzing the effect of identified risks on overall project objectives.”
  ~Practice Standard for Project Risk Management (PMI)
ON-TIME
ON-BUDGET
SCOPE
QUALITY

## Slide 37: Common Quantitative Risk Analysis Techniques
Decision tree analysis | A graphic tool depicting alternative choices as branches, multiple options for each alternative, & evaluating potential outcomes in terms of uncertainty and monetary value
Expected monetary value (EVA) analysis | A statistical technique to calculate present value of future outcomes to choose the best alternative
Failure mode and effect analysis (FMEA) | “A step by step approach for identifying all possible failures in a design, a manufacturing or assembly process, or a product or service.” ~Practice Standard for Project Risk Management (PMI)

## Slide 38: Common Quantitative Risk Analysis Techniques
Sensitivity analysis | A quantitative what-if risk analysis technique that presents comparative analyses of various desirable outcomes with respect to a financial measure or uncertainty…can be used to determine which risks have the most impact on the project outcomes or goals. i.e. Tornado diagram
Simulation | A technique that mimics real situations using uncertainties and assessing their impact on project objectives. i.e. Monte Carlo

## Slide 39: Criteria for Selecting a Quantitative Risk Technique Methodology
Use the explicit knowledge of project team members
Allow quick response
Help determine project cost & schedule contingency
Help foster clear communication
Easy to use & understand

## Slide 40: Risk Register Updates
Add probability of each risk occurring & its impact to the register
Document results of quantitative risk analysis in risk register

## Slide 41: Plan Risk Responses
Strategies for Responding to Risks
Risk Register Updates
  Plan risk responses – “the process of developing options and actions to enhance opportunities and reduce threats to project objectives.” ~Practice Standard for Project Risk Management (PMI)

## Slide 42: Strategies for responding to risks
Many projects use multiple strategies depending on combo of risks faced
(p. 375 in textbook)

## Slide 43: Breakout Session!
Come up with at least one specific example of how to use each of the eight risk response strategies listed in Exhibit 11.12

## Slide 44: Risk Register Updates
Keep register updated with results from risk response planning
Include any changes to the project schedule, budget, resource assignments & communications plan

## Slide 45: Summary
All projects have some risks
Risk planning should use an appropriate level of detail to plan for major risks
Risk planning begins with an understanding of project success
Risk management plan is part of the overall project management plan
Risk identification includes gathering information on potential risks

## Slide 46: Summary
Identified risks are documented in a risk register
Identified risks are analyzed
Risk response planning involves determining response to each major risk
Risk response strategies include avoid, transfer, mitigate, accept, research, exploit, share, & enhance

## Slide 47: Risk Management on a Satellite Development Project
Planning
Establish process for dealing with risk & change
Day-long clinic
Criteria for evaluating probabilities of occurrence
Compared methods to industry standards
Systematically working with the risks of the project allowed us to prepare responses to the risks if and when they occurred.
  PM IN ACTION

## Slide 48: Risk Management on a Satellite Development Project
Execution
Integrated approach to identification, analysis, & response to risks
Using a risk management database tool to log each risk as a record in the database
  PM IN ACTION

## Slide 49: Risk Management Worksheet
  PM IN ACTION

## Slide 50: Risk Management on a Satellite Development Project
Risk management reviews
Review logged risks, actions & impacts of risks
Review prioritized report of all project’s risks
Avenue to resolve high-priority risks of the project
Identification of potential risks for related projects
  PM IN ACTION

## Slide 51: PMBOK Exams
As PM, your goal is to complete your project on time, on budget, at an agreed upon level of quality, & to the satisfaction of your client and other stakeholders. Risks are anything that could impede—or help—you in this goal.
Remember that, according to PMI, project risks can be negative or positive.
Strategies for dealing with negative risks, or threats, are as follow: avoid, transfer, mitigate, research, & accept.
Strategies for dealing with positive threats, or opportunities are the following: exploit, enhance, share, research, & accept.
In creating a risk management plan, the first step is to identify all possible risks.
While it may seem counterintuitive, you do not want to plan for all risks.
Only the risks that emerge as “major” based on probability of occurrence & potential impact are actively planned for.
All projects make use of qualitative planning, & larger projects often proceed to quantitative planning (if may help you to remember that the “l” in qualitative comes alphabetically before the “n” in quantitative). Be familiar with the most common quantitative assessments.

## Slide 52: Casa de Paz Development Project
Brainstorm all risks you can imagine for Casa de Paz.
Qualitatively assess risks to determine big ones.
Create response plans for big risks.
Which are so big, they threaten the entire project (showstoppers)?